Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 08 October 2026 |
| --- | --- |
| Team ID | 9100SmartGirls |
| Project Name | Streamlining IT Procurement – Automating Standard Laptop Orders with Flow Designer |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Flow Automation | USN-1 | As an IT procurement team member, I can create a Flow Designer flow for standard laptop requests so that the process is automated. | 3 | High |  |
| Sprint-1 | Flow Automation | USN-2 | As an administrator, I can configure the Service Catalog trigger so that the flow starts for a laptop request. | 2 | High |  |
| Sprint-1 | Catalog Task Creation | USN-3 | As an IT team member, I can automatically create a Catalog Task for an approved Standard Laptop request. | 5 | High |  |
| Sprint-1 | Catalog Task Creation | USN-4 | As a hardware team member, I can receive the task with the laptop configuration description. | 2 | High |  |
| Sprint-1 | Task Assignment | USN-5 | As an IT administrator, I can assign the generated Catalog Task to the Hardware group. | 2 | High |  |
| Sprint-2 | Flow Assignment | USN-6 | As an administrator, I can attach the Standard Laptop Task flow to the Standard Laptop Service Catalog item. | 3 | High |  |
| Sprint-2 | Approval | USN-7 | As an IT procurement team member, I can process the Standard Laptop request through approval before the task is created. | 3 | High |  |
| Sprint-2 | Service Catalog | USN-8 | As a user, I can select Standard Laptop from Service Catalog and place an order. | 2 | High |  |
| Sprint-2 | Request Tracking | USN-9 | As an IT user, I can view order status and open the request details. | 2 | Medium |  |
| Sprint-2 | Validation | USN-10 | As an administrator, I can verify the Requested Item and Catalog Task status, description, and assignment group. | 5 | High |  |
| Sprint-2 | Documentation | USN-11 | As a project team member, I can document the completed automated workflow and its outcome. | 3 | Medium |  |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 14 | 6 Days | 08 Oct 2026 | 13 Oct 2026 | 14 | 13 Oct 2026 |
| Sprint-2 | 18 | 6 Days | 15 Oct 2026 | 20 Oct 2026 | 18 | 20 Oct 2026 |

Velocity:

For this project, the planned total story points are 32 across two sprints. The average velocity is calculated as total completed story points divided by the number of sprints.

Average Velocity = 32 / 2 = 16 Story Points per Sprint.

Number of Sprints = 2

Total Story Points = 14 + 18 = 32

Burndown Chart:

A burndown chart is a graphical representation of work remaining versus time. It is used here to track the remaining work for the ServiceNow automation sprint.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts